## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Ressource Planning
| Ressource Planning | Ressource Planning - Ressource
| Prios as Numbers | Ressource Planning - Prios as N
| Priorities | Ressource Planning - Priorities
First User Stories
| Table 1 | First User Stories

## Ressource Planning - Ressource
Ressource Planning
Topic | Priority | Prio-# | Responsible | Remarks | Status
Exchange Sue | Very High | 1 | Peter
Maintain existing Naos | Very High | 1 | Peter | Temperature problems (Judy) Arm movement (Luc)
Ball | Very High | 1 | Peter |  | Jul06: Sent e-mail and asked for price and shipping costs.
Own lockable room | Very High | 1 | Peter |  | Jul06: Clarified with Mr. Mörixbauer and Mr. Holzer that we can use a part of the room opposite to the music room (where the desks are currently stored). Room will be available by start of next school year.
Bitbucket repository | Very High | 1 | Sabina | Bauepete | Jul05: Bitbucket not feasible since max 5 team members are allowed. Repository at gitlab.htl-leonding.ac.at now set up. All team members have accounts and are member of the gitlab group. DONE.
Check SPL Site regularly | Very High | 1 | Viki | http://www.tzi.de/spl/bin/view/Website/WebHome
Chip Thomas Himmelbauer | Very High | 1 | Sabina
Summer access | Very High | 1 | Peter
Super soft green carpet (>= 6 * 5 m) | High | 2 | Peter
White color | High | 2 | Peter
Print 2016 rules | High | 2 | Meli
Construct one goal | High | 2 | Sabina
Buy 4 new batteries | High | 2 | Peter
LAN cables | High | 2 | Meli | Thomas Himmelbauer
Get tool set | High | 2 | Sabina | with Thomas
Get pin board | High | 2 | Peter
Get couch | High | 2 | Viki | Everybody asks!!!
Buy referee whistle | Medium | 3 | Viki
Name + Logo | Medium | 3 | Viki
Domain + Website | Medium | 3 | Meli | quack@roboducks-leonding.com, https://www.tierra.net/domains
Organize Robot Jour-Fixe w/ [Himmel]bauer | Medium | 3 | Peter
More stuff to the team | Medium | 3 | Peter
Buy four more Naos | Low | 4 | Peter
Nao Trikots | Low | 4 | Peter | Pink
Organize situations w/ different light | Low | 4
Get Thomas Himmelbauer to Japan | Low | 4
Acquire Sponsors | Low | 4 | Peter
First-Aid-Kit | Low | 4 | Viki
Team T-shirts | Low | 4 |  | # of team members (more than 5)

## Ressource Planning - Prios as N
Prios as Numbers
Prio | Prio-#
Very High | 1
High | 2
Medium | 3
Low | 4

## Ressource Planning - Priorities
Priorities
Very High | July 5 onwards
High | To be ready by August 1
Medium | From September onwards
Low | From December onwards

## First User Stories
Id | Epic | Name | Story | Acceptance Criteria | Priority | Story Points